EXHIBIT 2

SCOPE OF SERVICES

PROVISION OF QUALITY ASSURANCE & QUALITY CONTROL SERVICES

TABLE OF CONTENTS

1.	purPOSE	3

2.	DEFINITIONS AND ABBREVIATIONS	3

3.	FACILITIES DATA	3

3.1	Overview	3

3.2	FACILITIES	4

4.	REQuIREMENTS TO PERFORMANCE OF qa/qc SERVICES	8

4.1	Scope of Services	8

4.2	Specific scope of services	8

4.2.1	QA/QC Activities for Site Inspection Service for procurement packages	8

4.2.2	Management and Administration	9

4.3	Execution of SERVICES	12

4.4	Responsibility of CONTRACTOR	13

4.5	Project coordination, lines of communication and reporting responsibilities	14

4.6	CONTRACTOR personnel	15

4.7	Meetings and reporting	17

4.8	Non-conformance	17

4.9	Personnel safety	18

4.10	Close out Services	18

5.	codes AND STANDARDS	18

6.	RESPONSIBILITY OF THE CLIENT	18

6.1	The CLIENT is OBLIGED:	19

6.2	The CLIENT has the RIGHT:	19

7.	REQUIREMENTS TO SAFE PERFORMANCE OF WORKS	19

# purPOSE

In the event that CLIENT requests SERVICES, CLIENT shall send a quotation request to CONTRACTOR for submission of a quotation and proposed available PERSONNEL. If CONTRACTOR is selected for such a CALL-OUT event, the following applies:

The QUALITY ASSURANCE & QUALITY CONTROL (QA/QC) SERVICES for the Dai Hung Nam Project encompass all necessary QA/QC activities associated with the various phases of the project, including:

- Procurement

- Construction

- As-Built Drawings

- Final Documentation

CONTRACTOR shall act as the representative of PVEP-POC to perform QA/QC activities for ten (10) critical procurement Long Lead Items (LLIs) packages as well as other reimbursed packages under the EpCI scope of work.

# Overview

Dai Hung Nam (DHN) area is located in the southern part of Dai Hung oil field of Block 05-1(a), approximately 250 km from the coastline of the South-Eastern Vietnam and is situated in a water depth of 110 m (average). Block 05-1(a) has been operated by PVEP since 2003. The center of DHN is located approximately 3.5 km from the existing WHP-DH02 and 7.5 km from the current location of the FPU.

The location map of Block 05-1(a) is as hereunder in Figure 3.1.1.

Figure 3.1.1: Block 05-1(a) Field Location

# FACILITIES

The field facilities in Dai Hung Nam Field Development are as follows:

- New unmanned wellhead platform WHP-DHN located near WHP-DH02. WHP-DHN will be designed with 11 well slots for drilling by jack-up rig. Full wellstream of WHP-DHN will be routed to a Production Separator (on WHP-DHN) then the separated liquid is transported to FPU for further processing, a separated associated gas is exported to BK-TNG.

- Infield Pipelines:

- One liquid rigid pipeline, transporting separated liquid from WHP-DHN to FPU through subsea tie-in point of existing 10” liquid flowline from WHP-DH01 to FPU.

- One gaslift rigid pipeline, transporting gaslift from WHP-DHN to WHP-DH02.

- One export gas/source gas, transporting separated associated gas/source gas from WHP-DHN to subsea tie-in point of 16” existing export gas pipeline at WHP-DH02 and via versa.

- One water injection rigid pipeline, transporting water injection from FPU to WHP-DHN through subsea tie-in point of existing 8” water injection flowline from FPU to WHP-DH01.

- Modification works on WHP-DH02, WHP-DH01 and FPU for connection and processing.

Scheme of Dai Hung Nam Field Development is presented as below.

Figure 3.2.1: Dai Hung Nam Field Development Scheme

3.2.1 	Wellhead Platform WHP-DHN

The Jacket consist of the following component parts:

- The jacket shall be a 4-leg substructure located in a water depth of 108.70 m below MSL and secured to the seabed by 8 nos. skirt piles.

- Two (2) docking piles will be pre-installed at the Subsea Drilling Template. Afterwards, the jacket will be installed above the Subsea Drilling Template via the docking piles.

- The WHP-DHN jacket shall accommodate the following appurtenances:

| Items | Present Requirements | Future Requirements |
| --- | --- | --- |
| Conductors | - 7 nos. of 36” (914 mm) - 3 nos. of 30” (762 mm) - 1 no. of 20” (508 mm) | - |
| Risers | - 1 no. of 6” for Gaslift Riser - 1 no. of 8” for Water Injection Riser - 1 no. of 10” for Gas Riser - 1 no. of 10” for FWS Riser | - 2 nos. of 10” Risers |
| J-tube | - | - 1 no. of 10” J-tube |
| Boat Landing | - 1 main and 1 auxiliary at opposite direction (Row 1 & Row 2) | - |

The Topside shall comprise of the following primary process and utility systems:

- Wellheads (including WHCP and HPU).

- Manifolds (Production and Test manifold, Gaslift and Water Injection).

- Production Separator.

- Test Separator.

- Production Gas Cooler.

- Production Gas Scrubber.

- Gaslift Compressor Package.

- Pigging Facilities (Production Pig Launcher) & temporary Gas lift Pig Launcher.

- Flare system

- Closed Drain System.

- Open Drain System.

- Chemical Injection System.

- Back-up Chemical Injection System.

- Services and Potable Water System.

- Nitrogen Generation System.

- Fuel Gas System.

- Instrument Air System.

- Utility Air system.

- Gas Engine Generator.

- Standby Diesel Generator.

- Diesel System.

- Pedestal Crane.

- Power Distribution System.

- Future Booster Pump

- Deck Integrated Fire Fighting System.

WHP-DHN shall be connected with the existing facilities by the following pipelines:

- Liquid pipeline from WHP-DHN to FPU via WHP-DH01 export pipeline.

- Water injection from WHP-DH01 to WHP-DHN.

- Makeup /export Pipeline Gas from WHP-DH02 to WHP-DHN

- Export gaslift from WHP-DHN to WHP-DH02.

Spare spaces for Liquid booster pumps and Tie-in for future shall be provided.

Figure 3.2.1: 3D Modeling for Wellhead Platform WHP-DHN

3.2.2 	Infield subsea pipeline:

The scope of work for the subsea rigid pipeline systems of Dai Hung Nam Project includes:

8-inch Water Injection (WI) Pipeline ~ 9.3km from WHP-DH01 to WHP-DHN, including a riser at WHP-DHN, subsea tie-in spools at both pipeline ends and a crossing over existing 16-inch Gas Export Pipeline;

10-inch Production (FWS) Pipeline ~ 9.3km from WHP-DHN to WHP-DH01, including a riser at WHP-DHN, subsea tie-in spools at both pipeline ends, a crossing over existing 16-inch Gas Export Pipeline and a piggable wye at WHP-DH01;

10-inch Source Gas (SG) Pipeline ~ 3.3km from WHP-DH02 to WHP-DHN, including a riser at WHP-DHN, subsea tie-in spools at both pipeline ends and a subsea barred tee at WHP-DH02;

6-inch Gaslift (GL) Pipeline ~ 3.3km  from WHP-DHN to WHP-DH02, including a riser at WHP-DHN and subsea tie-in spools at both pipeline ends;

02 (two) 10-inch Future Risers at WHP-DHN.

3.2.3		Modifications

Modification works on WHP-DH02 and FPU for connection and processing.

3.2.4    Well Flowlines on WHP-DHN

There are 11 well flowlines including 08 production wells and 03 production wells/water injection wells as designed on WHP-DHN.

WHP-DHN will be completed with hook-up for 03 tie-back wells (DHN-4X, DHN-2X and DHN-1X) and maximum are 06 wells before First Oil, remaining wells will be completed hook-up at later stage in accordance with the tentative Drilling schedule as Attachment #5 – Drilling and Completion Schedule.

# REQuIREMENTS TO PERFORMANCE OF qa/qc SERVICES

## Scope of Services

The General scope of service is specified in summary table below:

|  | FACILITIES |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | WHP-DHN |  | Subsea Rigid Pipeline | WHP-DH02 and FPU Modification | WHP-DHN Well Flow lines |
|  | Jacket | Topside Facilities |  |  |  |
| Site Inspection Service for 10 procurement packages (Long Lead Items): Gas Lift Compressor, Structural Steel, Pedestal Crane, Gas Engine Generator and Standby Diesel Generator, E-House, Rigid Line pipe, Pressure Vessels, Chemical Injection Skid, Wellhead Control Panel, Main Valves | x | x | x | x | X |
| Site Inspection Service for Reimbursed packages under EpCI (list will be supplied as CLIENT Supply Data) | x | x | x | x | X |
| QA/QC services for other activities | X | X | X | X | X |

## Specific scope of services

### QA/QC Activities for Site Inspection Service for procurement packages

Upon the CLIENT’s requests and approval, CONTRACTOR shall be a representative for CLIENT responsible for performing inspection service at manufacturer site as requested by CLIENT based on the approved Vendor’s ITP (Inspection and Testing Plans), included but not limited to:

- Attend PIM (Pre-Inspection Meeting) and Audit at manufacturer.

- Perform inspection for materials.

- Review/Witness Welding Procedure Specifications (WPSs) and Welding Procedure Qualification Records (WPQRs)

- Review/Witness welder and welding operator qualification.

- Review/Witness Non Destructive Testing (NDT) included RT, UT, PMI, MI, PT,…

- Review/Witness MPQT.

- Witness Hydrotest, Leak test, Load test, Performance Test…

- Perform necessary fabrication survey (dimension, welding, painting,…) during fabrication and witness other tests during fabrication.

- Verify the manufacture progress.

- Perform inspection, witness, verify the results of Factory Acceptance Test (FAT) and other tests specified in the Vendor Inspection and Testing Plans.

- Carry on the final inspection and issue Inspection Release Note (IRN) including sign off on Final Certificates and Punch lists to acknowledge the goods are ready for Shipment.

- Report to the CLIENT in daily and propose solutions for any problems affecting quality and progress.

- Other activities as required by CLIENT.

### Management and Administration

- General

CONTRACTOR is responsible for professional execution of the SERVICES to ensure the FACILITIES are in compliance with the technical requirements and the applicable codes and standards routinely employed by an international provider of such services. CONTRACTOR shall provide all materials, inspection equipment and tools, reporting process and templates necessary to fully perform the SERVICES.

CONTRACTOR shall ensure all such Inspection Equipment is maintained in accordance with documented procedures and instructions including service checks and calibrations performed by Contractor.

CONTRACTOR shall provide competent, multi-discipline personnel or resources to verify a large range of inspections and tests, covering a broad range of disciplines and on a global scale. The inspections and tests undertaken by CONTRACTOR at worldwide locations shall ensure the quality of materials, structures, components and systems during procurement, construction and commissioning phases of the PROJECT comply with the PROJECT standards and regulations.

CONTRACTOR’s Project Coordinator shall liaise directly with CLIENT QA/QC Representative to coordinate all QA/QC Resources and Activities at the various WORK SITES.

- Organization and Key Personnel

CONTRACTOR shall submit Project Organization Chart that identifies its Personnel including their proposed base locations, source indicators (i.e Project Coordinator, Senior Engineer(s)/Inspector(s),…) based on the Scope of Service.

CONTRACTOR shall submit proposed personnel with clear full names, years of experience in oil and gas projects, CVs and qualifications/ certificates in accordance with Project Execution Plan and qualification requirement as Section 4.6. PERSONNEL.

CONTRACTOR shall designate its KEY PERSONNEL in its Organization Chart. KEY PERSONNEL shall be listed together with their position descriptions, responsibilities, authorities, and other information and shall not be removed or replaced from the PROJECT with prior CLIENT QA/QC Representatives Approval.

CONTRACTOR shall assign PERSONNEL who are fully qualified and competent for their respective positions approved by CLIENT are named in the Contract, all such named PERSONNEL shall not be removed without the written approval of CLIENT.

CONTRACTOR shall not designate any proposed Subcontractor personnel as “KEY PERSONNEL’’ (IE Project Coordinator nor Level Class I1 PERSONNEL as stated in section 4.6)

CONTRACTOR shall organize its resources to meet the demands. In response to CLIENT requirements, CONTRACTOR shall prepare a Call Off Work Order for approval by CLIENT covering all PERSONNEL that are deployed to the SERVICES.

CLIENT reserves the rights to mobilize whatever resources required from any third party if CONTRACTOR fails to timely discharge its obligations under the CONTRACT and all incremental costs associated with the mobilization and demobilization of a third party and performance of the SERVICES shall be back-charged to CONTRACTOR.

CONTRACTOR warrants that the SERVICES shall be performed efficiently, professionally and within the Contract Schedule. In the event that any of the SERVICES performed by CONTRACTOR is unsatisfactory, CLIENT will duly notify CONTRACTOR of the deficiencies and CONTRACTOR shall promptly rectify the deficiencies at its own costs. CLIENT reserves the rights to engage another party to rectify the deficiencies if CONTRACTOR fails to promptly do so upon notification and all costs associated with the rectification of the deficiencies by the other party shall be back-charged to CONTRACTOR.

- Services and Support

CONTRACTOR shall provide all visas, licenses, work permits, facilities, PPE, accommodation, transportation, computer, phone, IT equipment, services, etc. and support for their PERSONNEL to enable full execution of the SERVICES. CONTRACTOR shall be responsible for all travel and subsistence, accommodation, and other allowances required by CONTRACTOR PERSONNEL, except travel expenses related to travel to offshore WORK SITES.

CONTRACTOR shall promptly mobilize such facilities, services, IT equipment, and support so that they are available to CONTRACTOR PERSONNEL in a timely manner.

CONTRACTOR shall arrange and coordinate all travel, accommodation, formalities, insurance and the like for its PERSONNEL that are required by CLIENT to attend Vendor premises related to the procurement packages, and for travel to the transit point for travel to and from the offshore WORK SITE.

- Quality Deliverables Requirements

CONTRACTOR shall submit Project Execution Plan (PEP) and Project Quality Plan (PQP) which it has adapted to meet the requirements of Contract.

PEP – The PEP Documents shall collectively describe all major activities for the SERVICES, and how they are to be efficiently executed.

PQP – The PQP shall define Quality Policy, Quality Objectives and include quality system of CONTRACTOR.

- Execution Deliverables Requirements.

CONTRACTOR’s Project Coordinator shall prepare/check and issue formally to CLIENT QA/QC Representative Inspection Reports for the SERVICES. The Contents of these Reports will be agreed after Contract Award between CLIENT and CONTRACTOR Representatives.

This Report shall comprise verification of, by way of example but not limited to, the following: Inspection & Expediting Status, Documents Status, Fabrication/FAT Quality, ITP Verifying Quality, etc.

- Health, Safety and Environment (“HSE”)

CONTRACTOR shall submit evidence of its HSE Management Systems.

CONTRACTOR shall perform the SERVICES in strict conformance with CLIENT’s Health, Safety and Environmental (HSE) requirements, together with CONTRACTOR’s own procedures, and all applicable laws and regulations of all jurisdictions at all locations where these SERVICES are being performed.

CONTRACTOR shall ensure that all SERVICES are performed by, and under the supervision of experienced persons skilled in their respective area of expertise.

- CONTRACTOR’s IS0 9001 Quality Management System

CONTRACTOR shall submit a valid ISO 9001 Quality Management System Certificate.

CONTRACTOR shall be responsible for establishing, documenting, maintaining and applying a formal quality system for all SERVICES in accordance with PQP.

- Interface Management

The performance of the SERVICES may involve a number of interfaces with Certification/ Classification Authority, Vietnam Register, CLIENT and EpCI contractors & its subcontractors, vendors, and consultants engaged by CLIENT in development of the PROJECT.  CONTRACTOR shall coordinate with CLIENT and other parties engaged by CLIENT to identify, develop, manage, resolve and coordinate these external interfaces.

- Contract Schedule

CLIENT shall provide the initial Project Overall Schedule which includes procurement packages list and EpCI schedule to CONTRACTOR for reference only. Firm call out schedule shall be issued to CONTRACTOR once there is definite schedule for such inspection.

CONTRACTOR shall maintain a schedule based on the directions provided by CLIENT for the QA/QC SERVICES to be undertaken at the various WORK SITE.

- Document and Information Management

Document Management System:  During execution of the SERVICES, CONTRACTOR shall implement a comprehensive electronic document management system. Copies of the latest revisions of drawings, Technical Requirements, and other written information supplied by either CLIENT, EpCI Contractors, subcontractors or vendors shall be controlled.

Documentation at outlying WORK SITES:  During the performance of the SERVICES at all location(s) other than CONTRACTOR’s main office, CONTRACTOR shall maintain any latest drawings and written information relevant to SERVICES at such location(s).

## Execution of SERVICES

To ensure the smooth commencement of the SERVICES, it is essential and mandatory that CONTRACTOR appoint a Project Coordinator to liaise with CLIENT QA/QC Representative or his designate to develop activities requiring verification, and a plan to mobilize the necessary personnel to the site, administer the status of their review/ site survey inspection and to ensure that the SERVICES are completed within the specified time frame.

CONTRACTOR shall organize his workforce to meet CLIENT requirements. He shall ensure the mobilization and demobilization of the relevant personnel to meet CLIENT’s needs and timely advice CLIENT QA/QC Representative or his worksite Representative the findings of the verification and inspection/ audit in fulfilling CONTRACTOR's contractual obligations.

CONTRACTOR shall ensure that reports from offsite inspection, witness testing and audit shall be delivered to CLIENT QA/QC Representative or his worksite Representative within at least two (2) days of the completion of the inspection/witness testing and two (03) days of the completion of the audit. Flash report shall be delivered to CLIENT QA/QC Representative within one (1) day of the completion of the inspection/witness testing if required by CLIENT.

CLIENT shall define the level of SERVICES required. CONTRACTOR shall organize its resources to meet the needs. PVEP-POC reserves the rights to mobilize whatever resources required from any third party if CONTRACTOR fails to timely discharge its obligations under the CONTRACT and all costs associated with the mobilization and demobilization of a third party and performance of the SERVICES shall be back-charged to CONTRACTOR.

CONTRACTOR main source of schedule data will be from CLIENT who shall issue detailed engineering, procurement, fabrication, installation and commissioning schedules and updates. CONTRACTOR Project Coordinator shall ensure that these data are distributed and integrated at all levels and at all sites.

## Responsibility of CONTRACTOR

CONTRACTOR shall provide, as a minimum, such SERVICES to evidence the adequacy of the Site Inspection Service for procurement packages of the FACILITIES comply with all applicable CLIENT’s specification requirements or relevant of International Codes or Standards.

CONTRACTOR is deemed to have full knowledge of the International Classification Rules and shall be responsible for communicating directly with CLIENT QA/QC Representative to control QA/QC activities and arranging mutually satisfactory schedules for the performance of review/surveys/witness/inspection/testing activities.

CONTRACTOR shall appraise the project quality system, undertake surveys at manufacture worksites/fabrication worksites and its sub-contractors in order to verify compliance of all product, systems and manufacturing processes against CLIENT approved specifications, standards and codes.

SERVICES to be performed for each discrete phase of the project shall include all QA/QC activities necessary to verify the FACILITIES comply with CLIENT Specification Requirements, International Standards, International Rules and Regulations and current editions of the applicable Rules and Regulations for the Classification of Fixed Offshore Installations issued by International Classification Authorities.

CONTRACTOR shall provide all necessary qualifications and all head office support required to properly perform QA/QC activities.

CONTRACTOR shall be responsible for providing all necessary protective clothing, transportation, accommodation and subsistence for its personnel whilst working away from QA/QC SERVICE SUPPLIER’S head office whether at worksites in Vietnam or international worksites out of Vietnam and its sub-contractors.

CONTRACTOR shall liaise closely with CLIENT as necessary in order to diligently perform the SERVICES.

CONTRACTOR shall review the project Master Document Register and shall issue a schedule of documents that it wishes to receive for the purposes of either: Review/Audit, Inspection or other survey activities.

CONTRACTOR shall receive the required documents from CLIENT, directly from CLIENT’S other contractor’s, the precise methodology to be agreed between CLIENT and CONTRACTOR.

CONTRACTOR shall be responsible for performing all SERVICES necessary to verify the facilities at all project locations including the worksites and its sub-contractors where manufacturing, fabrication, installation and testing activities will be undertaken.

CONTRACTOR shall comply/ observe in all respects with CLIENT Health, Safety and Environment policies as set out.

CONTRACTOR shall perform the services as requested and agree to the turnaround durations as specified above. For services that are not indicated as above specified, CLIENT and CONTRACTOR shall mutually agree to a reasonable turnaround.

## Project coordination, lines of communication and reporting responsibilities

CONTRACTOR shall be responsible for coordinating the SERVICES with CLIENT QA/QC Representative or his worksite Representative at the various sites. CONTRACTOR shall communicate with and receive instructions from CLIENT QA/QC Representative or his worksite Representative directly on matters pertaining to the SERVICES.

To facilitate smooth communication flow and expedite document review turnaround, CONTRACTOR’s local and overseas offices participating in any of the SERVICES should have facsimile, E-mail and Internet facilities for routine communication, transmission of inspection/test/audit reports and monitoring of the progress of the SERVICES.

CONTRACTOR shall maintain a log of all the in-coming and out-going correspondence, its status, monitor the resolution of any outstanding issues concerning the SERVICES, and for proper document control in this regards, CONTRACTOR shall implement a dedicated electronic database system to meet this requirement. CONTRACTOR shall review the proposed system with CLIENT to explore the possibility of integrating CONTRACTOR's system with CLIENT’s system.

CONTRACTOR shall maintain a hard copy of all reports and certificates associated with the provision of the SERVICES and files for safe-keeping.

CONTRACTOR's representatives located at any of CLIENT’s Worksites shall coordinate the daily work program with CLIENT worksite Representative located at the same site. All activities associated with the SERVICES shall be reported and actioned locally as appropriate. For SERVICES that is performed at offsite locations, it is of paramount importance that any such SERVICES must be completed by the assigned personnel prior to the crew change or leave and proper hand-over instructions must be in place for the next in-coming crew / replacement. CLIENT has the right to refuse CONTRACTOR's personnel to go for leave or crew change if the hand-over is not done properly. CLIENT also has the right to refuse CONTRACTOR's PERSONNEL  to go for leave or crew change if, in CLIENT’s view, CONTRACTOR's PERSONNEL did not perform his obligations satisfactorily and rectification work is required. CLIENT shall not be responsible for the costs associated with these refusals for CONTRACTOR's PERSONNEL to go for leave or crew change.

To expedite the submission of the witness, audit and test reports of procurement packages, CONTRACTOR's PERSONNEL at the site shall transmit the reports to CLIENT’s worksite Representative and to CONTRACTOR Project Coordinator's office concurrently. The fastest means of transmission shall be used.

## CONTRACTOR personnel

CONTRACTOR PERSONNEL shall be permanently staffs or part time with signed agreement to demonstrate the proposed QA/QC SERVICE TEAM shall be established in accordance with requirement in Section 4 of this document.

CONTRACTOR personnel engaged in the SERVICES shall be experienced and competent for the required work scope. CONTRACTOR's personnel engaged and assigned to perform the review/witness/site survey inspection for fabrication and offshore sites in accordance with construction methodology/specifications/procedures/standards, experienced in the field works and competent with the construction works. They must meet the following minimum qualification and experience. Personnel who are assigned must have minimum experience and qualification stated below.

| Personnel Classification | Minimum Qualification & Experience Requirements |
| --- | --- |
| A. Project Coordinator |  |
| Project Coordinator | - Basic engineering degree and over fifteen (15) years of International working experience in the oil and gas industry, this includes at least five (5) years of managing QA/QC Services Activities. - Familiar with the onshore fabrication or offshore installation sites or at vendor's works, relating to inspections, fabrication, installation, testing and hook-up & commissioning of oil and gas facilities. |
| B. Engineer |  |
| Class I1 - Senior Engineers Senior Mechanical Engineer Senior Electrical Engineer Senior Instrument Engineer Senior Telecom Engineer Senior Piping Engineer Senior Pipeline Engineer Senior QAQC Engineer Senior Metallurgical Engineer | - Basic engineering degree and twelve (12) years of working experience in the oil and gas industry in relevant discipline respectively. - Familiar with the engineering design, fabrication, installation and hook-up & commissioning of oil and gas facilities in relevant discipline respectively. - For Senior QAQC Engineer position: Qualified for senior welding, NDT and painting certificate such as CSWIP, AWS, API, PCN, NACE, etc…, and deep understanding of QA/QC related quality system, regulations, codes and standards such as AWS, ASME, BS EN, API, ASTM, DNV, NACE, ANSI, etc… - Familiar with ISO 9001 system. |
| Class I2 - Engineers Mechanical Engineer Electrical Engineer Instrument Engineer Telecom Engineer Piping Engineer Pipeline Engineer QAQC Engineer Metallurgical Engineer | - Basic engineering degree and eight (8) years of working experience in the oil and gas industry in relevant discipline respectively. - Familiar with the engineering design, fabrication, installation and hook-up & commissioning of oil and gas facilities in relevant discipline respectively. |
| C. Inspector |  |
| Class II1 - Senior Inspectors Senior Welding Inspector Senior NDT Inspector Senior Coating Inspector Senior Piping Inspector Senior Electrical Inspector Senior Instrument Inspector Senior Telecom Inspector Senior Mechanical Inspector | - Diploma or trade certificate and twelve (12) years of working experience in the oil and gas industry in relevant discipline respectively in the fabrication yard or offshore sites or at vendor's works, relating to inspections, fabrication, installation, testing and hook-up & commissioning of the oil and gas facilities. - Inspectors shall be familiar with the equipment/packages assigned, and shall have a minimum of four (4) years experience in inspection and testing of similar equipment. - Qualified welding, NDT and painting certificate such as CSWIP, AWS, API, PCN, NACE, etc… - A deep understanding of QA/QC related regulations, data sheet, codes and standards such as AWS, ASME, BS EN, API, ASTM, DNV, NACE, ISA, ANSI, IEEE, NEMA, etc… - Familiar with ISO 9001system. |
| Class II2 - Inspectors Welding Inspector NDT Inspector Coating Inspector Piping Inspector Electrical Inspector Instrument Inspector Telecom Inspector Mechanical Inspector | - Diploma or trade certificate and eight (8) years of working experience in the oil and gas industry in relevant discipline respectively in the fabrication yard or offshore sites or at vendor's works and relating to inspections, fabrication, installation, testing and hook-up & commissioning of the oil and gas facilities. - Qualified welding, NDT and painting certificate such as CSWIP, AWS, API, PCN, NACE, etc… - Understanding of QA/QC related regulations, data sheet, codes and standards such as AWS, ASME, BS EN, API, ASTM, DNV, NACE, ISA, ANSI, IEEE, NEMA, etc… |

CONTRACTOR's PERSONNEL engaged in the SERVICES must be approved by CLIENT prior to the commencement of the work. Any change or replacement of personnel shall be subject to CLIENT’s approval. CONTRACTOR shall submit a timely copy of the relevant documents for CLIENT’s review so as not to interrupt the SERVICES.

CONTRACTOR's PERSONNEL must be motivated, willing to work overtime at short notice, and perform under pressure and changing priorities. In this regard, CONTRACTOR agrees to take good care of the welfare of its personnel, promptly pay their salary, and rewards commensurate with the expected hours of work, provide them with proper accommodation at their assigned location, transport and medical care.

## Meetings and reporting

CLIENT may also require CONTRACTOR to attend other ad hoc meetings either at the worksite or at CLIENT’s office. CLIENT worksite Representative at the various sites may request CONTRACTOR's PERSONNEL assigned to the site to attend other coordination or clarification meetings concerning the SERVICES.

CLIENT QA/QC Representative may request that CONTRACTOR issue a the progress report if any.

## Non-conformance

CONTRACTOR shall inform CLIENT immediately when a non-conformance part of the work is identified.

CONTRACTOR shall maintain a log of all the non-conformances and monitor their proper rectification. The log shall provide the details of the non-conformance, the contract specification paragraph relating to the non-conformance, who initiated the non-conformance report, the date of the non-conformance report, the date rectification was completed, the date of approval of non-conformance being rectified or CLIENT’s waiver of compliance, and details of any material required to enable completion, including the purchase order reference and the estimated date of material arrival on site.

CONTRACTORhas no authority to accept any non-conformity or to authorize deviations to the contract specification requirements. Only CLIENT is authorized to accept non-conformities or deviations. The Non-Conformance Report (NCR) status shall be issued weekly to CLIENT QA/QC Representative.

CONTRACTOR shall steward, monitor and follow up with the close-out of all non conformances.

## Personnel safety

CONTRACTOR warrants that all its personnel are fit for the SERVICES and have received the appropriate approved safety training courses (where applicable) before commencement of the SERVICES at the onshore fabrication and offshore installation sites. The type of training courses are:

- Vendor(s)' Safety Orientation courses.

- Safety Induction

- Scaffold Safety

- Radiation Safety

- Electrical Safety

- …

CONTRACTOR shall provide to its personnel the required personal protective equipment (PPE) such as safety boots, hard hat, safety glasses, ear plugs, full body harness, respiratory mask, etc. The cost to provide personnel safety training and provision of PPE and hand tools to QA/QC SERVICE SUPPLIER's personnel are included in the rates and are not separately reimbursable by CLIENT.

Any CONTRACTOR's PERSONNEL who fail to comply with CLIENT Vendor(s)' safety regulations at the worksite will be replaced and barred from all PVEP-POC’s projects.

CONTRACTOR's PERSONNEL  travelling offshore to CLIENT’s facilities shall have the safety and medical qualifications.

## Close out Services

CONTRACTOR shall close out services as contract term.

# codes AND STANDARDS

For QA/QC activities of FACILITIES, it is guided at least in FEED design basis of Dai Hung Nam Project, and the international and Vietnamese rules and standards.

# RESPONSIBILITY OF THE CLIENT

## 6.1	The CLIENT is OBLIGED:

On demand of the CONTRACTOR to give it the information and documentation necessary for performance of work.

On inquiry of the CONTRACTOR to create conditions for presence of its inspectors with the purpose of performing supervision both on onshore base and offshore, at any stage of construction.

To assist the CONTRACTOR in the performance of consultations and advisory meetings.

## 6.2	The CLIENT has the RIGHT:

To require the CONTRACTOR perform the SERVICES within the scope of the present Technical Requirements at a high technical and qualitative level.

To require CONTRACTOR list any delays and difficulties which can affect terms and quality of performance of work, with the indication of the reasons.

During performance of work to submit any requests on changes and additions in scope and terms of work performance.

To submit any requests to the CONTRACTOR about convocation, if necessary, consultations and realization of advisory meetings.

# REQUIREMENTS TO SAFE PERFORMANCE OF WORKS

The CONTRACTOR at realization of QA/QC activities should carry out rules on safe performance of works and according to Socialist Republic of Vietnam Legislation on protection of labors.