# Chapter V.

# SCOPE OF SUPPLY

SECTION 1. SCOPE AND SCHEDULE OF GOODS SUPPLY

- Scope of goods supply:

Package 14: Supply and transportation of pipe steel towers (Steel tube Tower):

| No. | List of Goods |  |  |  | Unit | Quantity (Total Weight (kg)) | Goods Description | Project location | Delivery Schedule |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | List of Goods | Sym bol | Nunber of Steel tower | Weight/ 1 Steel tower |  |  |  |  | Earliest (day) | Latest (day) |  |
| (a) | (b) | (c) | (d) | (e) | (f) | (g)=(d)x(e) | (h) | (i) | (k) | (l) | (m) |
| 1 | 220kV 4-circuit pipe steel tower | NO242B-60 | 1 | 106 680.20 | kg | 106 680.20 | According to Section III, Section 5 of Bidding document | Nghe An province | 110 | 150 |  |
| 2 | 220kV 4-circuit pipe steel tower | NO242B-72 | 1 | 129 235.12 | kg | 129 235.12 |  |  |  |  |  |
| 3 | 220kV 4-circuit pipe steel tower | NO242B-78 | 2 | 143 426.33 | kg | 286 852.66 |  |  |  |  |  |
| 4 | 220kV 4-circuit pipe steel tower | NO242B-84 | 2 | 152 733.60 | kg | 305 467.21 |  |  |  |  |  |
| 5 | 220kV 4-circuit pipe steel tower | NO242B-94L8 | 1 | 181 498.88 | kg | 81 498.88 |  |  |  |  |  |
| Total |  |  |  |  | kg | 1 009 734.07 |  |  |  |  |  |

Note:

- The approved bid estimate sets the VAT at 10%, and the bidder's VAT offer matches the approved estimate.

- Column (e): Weight/ 1 steel tower: The weight of the steel tower mentioned above is the weight of black steel (excluding the weight of bolts, nuts, and galvanizing) minus the weight of beveling and bolt hole punching. Bidder will supply the complete set of finished galvanized steel pipe towers (including all types of bolts) and transport them to the construction site's warehouses

- Column (g): Quantity (Total Weight (kg): The total weight of the steel tower mentioned above is the weight of black steel (excluding the weight of bolts, nuts, and galvanizing) minus the weight of beveling and bolt hole punching. The bid price must include all galvanizing costs, a complete set of bolts, nuts, and washers for the final finished steel tower, and the cost of replacing any steel bars that need to be refabricated during testing, as stipulated in the Regulations on the Design and Fabrication of Steel Poles and Bolt-Connected Steel Structures Used for Power Lines and Substations within the Vietnam Electricity Group (EVN), issued under Decision No. 428/QD-EVN dated March 26, 2025, by the Vietnam Electricity Group, and transportation costs to the construction site's warehouses (including unloading costs at the construction site).

- Bidder is responsible for painting the towers that are required to be painted according to the tender documents, and there will be no additional costs (this is included in the bid price).

- Detailed lists of each type of steel for each tower type are included in the drawings.

- The quoted price includes the cost of unloading at the construction site.

- Fixed-price contract: with the unit of weight being kilograms;

- The quantity of steel towers shown in the attached bidding documents is for reference only. The actual quantity of steel towers will be adjusted based on the approved post-fabrication steel towers quantity table of the contractor. The contract payment value will be adjusted accordingly based on the quantity of black steel (ungalvanized steel, excluding bolts, nuts, washers, minus the weight of beveling and bolt hole punching) of the steel towers as shown in the approved as-built drawings after the steel tower fabrication is completed (clearly stating the weight of black steel towers and the weight of finished steel towers) multiplied by the contract unit price.

- Furthermore, if the aforementioned items are needed for the project, the Northern Power Project Management Board will base its procurement on the winning bid results to make additional purchases.

- The winning bidder is obligated to provide Party A with a complete set of electronic documents (scanned to PDF files: bid documents and related materials during the bidding process, negotiation documents, contract, contract appendices, payment documents, drawings, as-built drawings, completion acceptance reports, and all other relevant documents during the contract execution process…) along with the paper documents.

- The bid price includes the contractor's costs for managing materials and equipment.

- Delivery Schedule Column (k) and Column (l): the earliest and latest delivery times for the contractor to the buyer. Detailed schedule for the columns as required in Item II (below).

II. Delivery schedule:

The steel towers supply schedule for this contract is within 150 days from the effective date of the contract, including:

+ Phase 1: 20% of the number of towers as specified in the contract package, to be supplied within 110 days from the effective date of the contract;

+ Phase 2: 40% of the number of towers as specified in the contract package will be supplied within 130 days from the effective date of the contract;

+ Phase 3: 40% of the number of towers as specified in the contract will be supplied within 150 days from the effective date of the contract.

(The specific types of towers to be supplied in each batch will be finalized during contract negotiations.)

III. Delivery Location:

All goods will be delivered to the warehouse of the construction contractor along the Quynh Luu 500kV substation and connecting power line Project in Nghe An province (Exact warehouse locations will be determined during contract execution).

IV. Important Notes:

+ The contractor commits to delivering the towers in complete sets with each delivery, including all types of bolts. In case of failure to deliver them in complete sets, the Employer has the right to refuse acceptance of the towers.

+ During the construction, erection of towers, tensioning of wires, or operation (during the warranty period), if any defects due to manufacturer's fault are discovered, the contractor must correct these defects within 4-7 days of receiving written notification from the Employer.

+ For any delays in the quantity of work that the contractor fails to rectify within 10 days, Party A will hire another pole manufacturer to produce them, and all costs will be borne by the contractor according to the requirements of the replacement manufacturer without further negotiation.

+ The bidder must provide a complete quotation regarding the quantity, tower code, unit, and weight of steel for all items within the scope of supply as stated in Section 1.1 – Scope of Goods Supply.

Based on the overall construction progress, the detailed tower handover schedule will be agreed upon during the contract negotiation and execution process (in accordance with the land clearance schedule and construction schedule).

Notes regarding transportation :

The Contractor shall commit to complying with the requirements stipulated in “Directive No. 1095/CT-TCDBVN dated 21 March 2014 on vehicle load inspection on national highways in Vietnam”.